## Project Plan
BCM One — Nectar DXP ¦ Real Time CDR Enrichment, Stitching & Analytics
Sep 14, 2026 → Jan 25, 2027 ¦ 20 Weeks (18 build/integration + 2 post-launch support) ¦ SkyConnect · CoreConnect · Sonus SBC ¦ 7 People
Task / Deliverable | Owner | W1 Sep 14 | W2 Sep 21 | W3 Sep 28 | W4 Oct 5 | W5 Oct 12 | W6 Oct 19 | W7 Oct 26 | W8 Nov 2 | W9 Nov 9 | W10 Nov 16 | W11 Nov 23 (Thanksgiving) | W12 Nov 30 | W13 Dec 7 | W14 Dec 14 | W15 Dec 21 (Christmas) | W16 Dec 28 (New Year) | W17 Jan 4 | W18 Jan 11 | W19 Jan 18 | W20 Jan 25
DEVOPS PRE-REQUISITES (must be ready before Aug 24)
Databricks workspace · Unity Catalog · IAM roles · cluster policies | dbSeer
AWS S3 buckets · ElastiCache Redis · VPC networking · security groups | Nectar DevOps
Team access — workspace · VPN · MFA · AWS console for all 7 people | Nectar DevOps
Confluent Kafka cluster · Schema Registry enabled · topics created | Nectar DevOps
NECTAR CONNECTOR PRE-REQUISITES (all 3 sources writing to Kafka by Sep 14 — Week 4)
SkyConnect (NetSapiens) → Kafka · adds customer_id · datacenter_id | Nectar
CoreConnect (Asterisk) → Kafka · adds customer_id · datacenter_id | Nectar
Sonus SBC → Kafka · CDR export · adds tenant context fields | Nectar
All 3 connectors validated · real data flowing · schemas confirmed | Nectar
▶ Nectar connector gate — Sep 14 (W4) · all 3 sources live · implementation start confirmed
PHASE 1 — DISCOVERY & REQUIREMENTS (Sep 14 – Sep 28, Weeks 1–3)
Session 1 — Stitching logic · session definition · SIP leg rules | SA+PM
Session 2 — Enrichment requirements · geo · carrier · codec · tagging | SA+PM
Session 3 — Existing Nectar alert types · alert functionality review | SA+PM
Session 4 — Alerting requirements · thresholds · windows · routing | SA+PM
Session 5 — Tenant/partner/customer structure · L0/L1/L2 · 2700 partners | SA+PM
Session 6 — New UI requirements · existing UI modifications needed | SA+PM
Session 7 — Conversation Journey · cross-source correlation design | SA+PM
Session 8 — Reporting · 4-5 rollup views · 3-4 dashboards Phase 1 | SA+PM
SkyConnect field reduction — 85 fields hot store vs cold archive | SA
CoreConnect mediation CDR levels — confirm schema scope for connector | SA
Three-level RBAC specification — L0/L1/L2 RLS policy design | SA
Session acceptance criteria — cross-source stitching test scenarios | SA+PM
A1: Kafka connectivity · schema registry · review all 3 CDR schemas | A1
C: Lakebase provisioning · UC workspace setup | C
B: Redis connectivity · existing Nectar alert worker review · key design | B
▶ Discovery readout — end of Week 3 · Sep 11 · all requirement docs delivered · Sep 14 build start
PHASE 2 — PRODUCTION BUILD (Oct 5 – Dec 7, Weeks 4–13)
A1: Bronze — SkyConnect · NetSapiens 85-field · record classification | A1
A1: Bronze — CoreConnect · Asterisk 37-field · multi-leg dedup | A1
A1: Bronze — Sonus SBC · bespoke timestamp parser · UTC normalise | A1
A1: ENRICH — broadcast joins · hierarchy · geo · carrier · hot reload | A1
A1: SCORE — threshold scoring · Redis INCR · idempotency | A1
A1: Job monitoring · CloudWatch dashboards | A1
A2: Silver — SkyConnect + CoreConnect session assembly · Delta MERGE | A2
A2: Silver — Sonus SBC cross-source correlation · synthetic correlation_id | A2
A2: Silver — late records · watermark · unmatched record handling | A2
A2: Lakebase SYNC — LTAP native · 60s SLA · 90-day partition mgmt | A2
B: Alert Type 1 — device event fast path · BRONZE classification · Redis | B
B: Alert Type 2 — registration · per-record · post-ENRICH · Redis INCR | B
B: Alert Type 3 — DXP/Nectar score · post-Silver · session namespace | B
B: Alert worker HA · leader election · EventBridge · all alert types | B
C: Reference data Delta tables — carrier · codec · geo · refresh pipeline | C
C: Unity Catalog 3-level RBAC · L0/L1/L2 RLS · 2700 partners · 90K cust | C
C: Gold aggregations · 4-5 rollup views · L0/L1/L2 materialised views | C
C: Dashboards — 3-4 reports · embed in UI · per reporting spec | C
C: Tenant isolation penetration testing · cross-tenant boundary validation | C
QA: Bronze schema validation — all 3 CDR sources · field mapping accuracy | QA
QA: Cross-source stitching correctness · correlation confidence · unmatched | QA
QA: Alert testing — Type 1/2/3 · threshold accuracy · EventBridge routing | QA
QA: L0/L1/L2 RBAC boundary testing · 2700 partner isolation | QA
QA: Volume testing · 35M records/day · 48hr sustained run | QA
QA: End-to-end testing · all 3 sources · stitching · alerting · dashboards | QA
UI team: Lakebase connection · RBAC queries · conversation journey view | UI+SA
◆ W6 — Bronze live all 3 sources · Alert Type 1 complete | [6 empty] | ◆
◆ W9 — ENRICH + SCORE running · Silver assembly stable | [9 empty] | ◆
◆ W11 — Silver cross-source stitching complete · Gold running | [11 empty] | ◆
◆ W14 — Development complete · volume tested · dashboards · UI ready | [13 empty] | ◆
PHASE 3 — INTEGRATION & GO-LIVE (Dec 14 – Jan 11, Weeks 14–18)
Live producer integration — all 3 sources · edge case handling | A1
Pipeline self-validation — completeness · leg counts · correlation rates | QA
End-to-end alert validation on live data — all 3 alert types | B
Documentation · Runbook · on-call procedures | SA
Tenant cutover · go-live validation · client sign-off | All
Go Live | [18 empty] | ◆
◆ W17 — Live data validated · documentation complete · ready for go-live | [17 empty] | ◆
🚀 GO-LIVE — January 11, 2027
Post-Production Support — monitoring · issue resolution · handover | All

## Sheet1
Talal | B
AbdelRehman | A1
Juan | A2
Vinicius | QA
Mohammad K | C
Omar | PM

## Legend
Role | Colour
SA — Solution Architect
A1 — Sr Engineer Streaming 1 · Bronze/Enrich/Score
A2 — Sr Engineer Streaming 2 · Silver/Lakebase
B — Sr Engineer Alerting/Redis
C — Sr Engineer Lakebase/UC/Gold/Dashboards
QA — QA Engineer
PM — Project Manager (50%)
All — Full Team
Nectar — Nectar Team (connectors)
dbSeer — dbSeer team
UI+SA — UI team + SA